OIL/PLNG/54/2/1/2026/71					                  17th March, 2026

Ministry of Petroleum and Natural Gas

Kartavya Bhawan-03, Janpath

New Delhi - 110001                                                                Kind Attn: Shri K. Reguram

Under Secretary (Exploration Division)

Sub: Rajya Sabha Provisionally Admitted Starred/Unstarred Question D. No. S8046 for 23.03.2026

Regarding “Anveshan across seven sedimentary”

Ref.  Your email dated 12.03.2026

Sir,

Reference above, our reply to the above Rajya Sabha Question is as follows:

| Will the Minister of Petroleum and Natural Gas: Q.(a) The details of the ongoing exploration activities being undertaken under Mission Anveshan across seven sedimentary basins, along with their current status and expected outcomes; | Answer to Q(a): MoPNG may reply suitably. Seismic Campaign Under Mission Anveshan (MA): For the comprehensive appraisal of India’s sedimentary basins, the Government of India, under Mission Anveshan, has initiated 2D seismic profiling across seven onland sedimentary basins. Oil India Limited has been entrusted with acquiring approximately 9,400 LKM of 2D seismic API in the hitherto unexplored regions of the Rajasthan and Ganga-Punjab basins, spanning the states of Rajasthan, Punjab, Bihar, and Uttar Pradesh. Seismic data acquisition began on 29th October 2024, and as of 10th March 2026, a total of 8,104.68 LKM has been completed, with survey work continuing. The areas wise plan vis-à-vis achievements of 2D Seismic data acquisition under Mission Anveshan (MA) are enlisted below. AREA; PLAN; Achievement; % Achieved. Area - 1: Rajasthan; 4300.00; 3714.96; 86.39. Area - 2: Ganga Punjab; 5100.00; 4389.72; 86.07. Total Project; 9400.00; 8104.68; 86.22. As data acquisition remains ongoing, processing and interpretation of the seismic data will follow upon completion. This will aid in identifying potential hydrocarbon leads and prospects post seismic API cycle, supporting further exploration activities including drilling, as part of India's initiatives to bolster domestic oil and gas resources from these frontier basins. |
| --- | --- |
| Q.(b) Whether the Government has taken any steps to ensure environmental safeguards and sustainable practices during large-scale seismic mapping and exploration under the Open Acreage Licensing Programme (OALP); and | Answer to Q(b): MoPNG may reply suitably. As far as Oil India Limited (OIL) is concerned, it conducts seismic acquisition campaigns with zero damage to local fauna and flora by strictly adhering to standard operating procedures (SOPs). The company minimizes its operational footprint across OALP blocks during seismic surveys and drilling, safeguarding surrounding ecosystems while maximizing exploration efficiency. OIL is committed to sustainable practices that balance aggressive hydrocarbon exploration in OALP acreages with minimal environmental impact, while ensuring full regulatory compliance and ecological preservation. |
| Q.(c) The projected timeline and estimated investment inflows expected from OALP Round X, and how these efforts align with India’s broader goal of energy self-reliance? | Answer to Q(c): MoPNG may reply suitably. The OALP-X bid round, launched by the Government of India on February 11, 2025, offers 25 blocks across 13 sedimentary basins, spanning 1,82,589.21 sq. km, with a bid submission deadline of May 29, 2026. While specific projected timelines for awards and investment inflows are not immediately known, the round aims to accelerate exploration and attract significant capital to boost domestic hydrocarbon exploration & production. As far as Oil India Limited (OIL) is concerned, it actively evaluating opportunities in OALP-X to broaden its exploration footprint across Indian basins, supporting national targets for energy security. |

Yours faithfully,

OIL INDIA LIMITED

(Kishore Kumar Baishya)

Chief General Manager (Planning)

For Chairman & Managing Director