OIL/PLNG/54/2/2/2025/34					                    30th July, 2025

Ministry of Petroleum and Natural Gas

Shastri Bhawan

New Delhi-110001

Kind Attn: Satpal Yadav

Assistant Section Officer(ONG I & ONG V)

Sub: Rajya Sabha Provisionally Admitted Unstarred Question Dy. No. S1030 for 04.08.2025

Ref.  Your email dated 22.07.2025

Sir,

Reference above, our reply to the above Rajya Sabha Question is as follows:

| Q.(a) The number of oil and gas exploration blocks awarded under OALP that remain non-operational as of June 2025 | Answer to Q(a): DGH/MoPNG may reply suitably. As far as Oil India Limited (OIL) is concerned, one Block awarded under OALP Round III in the state of Nagaland has remained non-operational due non-grant of Petroleum Exploration License (PEL) by the state government. The Revenue Sharing Contract (RSC) for the Block was signed with GoI on 16th July 2019, however, PEL is yet to be granted. |
| --- | --- |
| Q.(b) Whether lack of environmental and regulatory clearances has delayed progress | Answer to Q(b): DGH/MoPNG may reply suitably. As far as OIL is concerned, exploration activities in a number of OALP blocks have suffered delays due to the delay in the grant of statutory clearances such as Forest Clearance (FC), National Board of Wildlife Clearance (NBWL), Coastal Regulation Zone (CRZ) Clearance etc. In addition to above, in few of the Blocks the grant of regulatory clearance for Consent to Establish (CTE) and Consent to Operate (CTO) also suffered delays which affected the progress of planned exploration activities in the Blocks. In addition, delay in Aviation Research Centre (ARC) Clearances for drilling sites also delayed progress in Assam. |
| Q.(c) Whether private operators have exited or surrendered awarded blocks; | Answer to Q(c): DGH/MoPNG may reply suitably. |
| Q.(d) The investment lost or stalled due to delays in operationalisation; and | Answer to Q(d): DGH/MoPNG may reply suitably. OIL has actively participated in all recent bid rounds of Open Acreage Licensing Policy (OALP) and Discovered Small Fields (DSF) under Hydrocarbon Exploration Licensing Policy (HELP) and has significantly increased its domestic acreages. Presently, OIL has 32 nos. of OALP Blocks (Northeast-17, Rajasthan-3, Odisha-4, Gujarat-1, Andaman shallow offshore-2, Kerela Konkan shallow offshore-1, Mahanadi Ultradeep-2 & KG Ultradeep-2) covering 87,432 sq.km and 3 nos. of DSF Blocks covering 208 sq.km across eight sedimentary basins. So far, OIL has completed drilling of 14 nos. of onshore exploratory wells (5 in Rajasthan, 5 in Odisha and 4 in Assam) in 9 (nine) OALP blocks, and one shallow offshore exploratory well in Andaman Basin. However, drilling activities are yet to commence is some of the blocks due to non-receipt of PEL (Petroleum Exploratory Licence) and other clearances. Apropos above, till date there is no investment lost or stalled in any of the blocks. |
| Q.(e) What steps the Government is taking to streamline approvals and attract exploration? | Answer to Q(e): DGH/MoPNG may reply suitably. |

Yours faithfully,

OIL INDIA LIMITED

(Kishore Kumar Das)

Chief General Manager (Planning)

For Chairman & Managing Director